## defects
Defect ID | Test Case ID | Defect Summary | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
DEF-01 | TC-08, TC-09 | Cloudflare rate limiting during parallel execution | While executing multiple UI tests in parallel, ParaBank temporarily blocked access and displayed Cloudflare Error 1015 (Rate Limited) | 1. Run UI test suite with multiple workers enabled 2. Execute account creation and transfer scenarios repeatedly 3. Observe application response | Application should allow test execution and complete all scenarios successfully | Cloudflare Error 1015 displayed and some tests failed due to temporary access restriction | Medium | P2 | Closed
Root Cause
ParaBank demo application applied rate limiting when multiple automated requests were executed simultaneously from the same IP address.
Resolution
Playwright configuration was updated to execute tests using a single worker:
workers: 1
This prevented excessive concurrent requests and stabilized test execution.
Retest Result
All 18 automated test cases executed successfully after the configuration change.
Status updated to Closed.
Defect ID | Test Case ID | Defect Summary | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
DEF-02 | TC-03, TC-04, TC-05 | Static account ID returned invalid response | API validation tests were using a hardcoded account ID which no longer existed in the application database | Execute API test suite using account ID 13566 | API should return valid account information | API returned HTTP 400 Bad Request | Low | P3 | Closed
Resolution
Static account dependency was removed and dynamic account creation was introduced before validation.
Retest Result
API tests passed successfully using dynamically generated account IDs.